## Risk Register
Control ID | Domain | Control Description | Asset Name | Subscription | Resource Group | Risk Category | Likelihood (1-5) | Impact (1-5) | Risk Score (LxI) | Severity (Low/Med/High/Critical) | Compliance Mapping (CIS/NIST/ISO) | Evidence | Current Status (Open/Closed/In Progress) | Owner | Target Remediation Date | Comments
AZ-IAM-001 | Identity & Access | MFA not enforced for all users | Entra ID Tenant | Prod-Sub | N/A | Identity Compromise | 4 | 5 |  | Critical | CIS 1.1 / NIST IA-2 | Screenshot of CA policy | Open | IAM Team | 2026-03-30 | High priority
AZ-NET-002 | Network Security | NSG allows 0.0.0.0/0 on port 3389 | VM-Prod-01 | Prod-Sub | RG-Prod-Compute | External Exposure | 5 | 5 |  | Critical | CIS 5.2 / NIST SC-7 | NSG rule export | Open | Cloud Ops | 2026-03-15 | Immediate fix required
AZ-STO-003 | Data Security | Storage account public access enabled | stproddata01 | Prod-Sub | RG-Prod-Data | Data Exposure | 4 | 5 |  | High | CIS 3.1 / NIST AC-3 | Storage config export | In Progress | Storage Team | 2026-04-10 | Private endpoint planned

## Control Checklist
Control ID | Domain | Control Description | Implemented (Yes/No) | Evidence | Remarks
AZ-GOV-001 | Governance | Management group hierarchy defined
AZ-IAM-010 | Identity & Access | PIM enabled for privileged roles
AZ-NET-015 | Network Security | Azure Firewall deployed
AZ-CMP-005 | Compute | Disk encryption enabled for all VMs
AZ-LOG-002 | Monitoring | Defender for Cloud enabled